## Trang tính1
Tasks Name | Start Build | Finish Build | % Build | Names | Start Testing | Finish Testing | % Testing | Names | Notes
html page register | 2022-10-10 | 2022-10-12 | 100% | Trần Trung Thiên | 2022-10-13 | 2022-10-13 | 100% | Trần Trung Thiên
Code js, api page regiter | 2022-10-14 | 2022-10-16 | 100% | Trần Trung Thiên | 2022-10-17 | 2022-10-17 | 100% | Trần Trung Thiên
Quay youtube | 2022-10-17 | 2022-10-17 | 100% | Trần Trung Thiên | 2022-10-18 | 2022-10-18 | 100% | Trần Trung Thiên
Create project: Build folders, files, images... Tạo repo trên git hub và upload. | 2022-10-04 | 2022-10-04 | 100% | Nguyễn Anthony | 2022-10-04 | 2022-10-04 | 100% | Nguyễn Anthony
html 2 pages: index and detail | 2022-10-06 | 2022-10-07 | 100% | Nguyễn Anthony | 2022-10-08 | 2022-10-08 | 100% | Nguyễn Anthony
Code js for page index and page detail | 2022-10-08 | 2022-10-12 | 100% | Nguyễn Anthony | 2022-10-14 | 2022-10-15 | 100% | Nguyễn Anthony
Deploy project | 2022-10-17 | 2022-10-17 | 100% | Trần Trung Thiên | 2022-10-17 | 2022-10-17 | 10% | Trần Trung Thiên